## Datix listing report
Risk Register - Open Approved Radiology Services Risks - 4th January 2024
ID | Opened | Division | Principal objectives | Title | Likelihood (current) | Consequence (current) | Rating (current) | Likelihood (Target) | Consequence (Target) | Rating (Target) | Next Review Date
3665 | 2023-01-25 | Shared Services (Radiology and Pathology Services) | Patients | CT Referred from the Accident and Emergency Department | 3 Possible | 4 Major | 12 | 2 Unlikely | 2 Minor | 4 | 2024-04-01
3641 | 2022-12-09 | Shared Services (Radiology and Pathology Services) | Patients | Delay to patient treatment due to lack of medical illustration cover | 5 Almost Certain | 3 Moderate | 15 | 2 Unlikely | 2 Minor | 4 | 2024-01-11
3563 | 2022-07-19 | Shared Services (Radiology and Pathology Services) | People | DVT scans on Wrightington in patients | 3 Possible | 4 Major | 12 | 1 Rare | 4 Major | 4 | 2024-03-28
3506 | 2022-04-06 | Shared Services (Radiology and Pathology Services) | People | NHS.NET DELAY FROM REQUEST TO EXAMINATION | 2 Unlikely | 3 Moderate | 6 | 1 Rare | 4 Major | 4 | 2024-07-01
3491 | 2022-07-04 | Shared Services (Radiology and Pathology Services) | Patients | Radiography Equipment Over 10 Years Old | 4 Likely | 3 Moderate | 12 | 3 Possible | 2 Minor | 6 | 2024-04-01
3792 | 2023-07-02 | Shared Services (Radiology and Pathology Services) | Patients | Radiology/Vascular IT Connectivity between WWL and Lancashire Teaching Hospitals | 3 Possible | 4 Major | 12 | 2 Unlikely | 3 Moderate | 6 | 2024-04-01
3700 | 2023-02-28 | Shared Services (Radiology and Pathology Services) | Patients | Reduction or complete loss of isotope supply due to worldwide Molybdenum 99 (Mo99) shortage. | 2 Unlikely | 4 Major | 8 | 1 Rare | 4 Major | 4 | 2024-04-01
3136 | 2021-03-05 | Shared Services (Radiology and Pathology Services) | Performance | Symptomatic breast imaging: Excessive waiting times from referral to exam. Failure to achieve 28-day faster diagnostic standard. | 3 Possible | 3 Moderate | 9 | 2 Unlikely | 3 Moderate | 6 | 2024-04-01
2751 | 2019-11-29 | Shared Services (Radiology and Pathology Services) | Performance | Ultrasound service provision and expansion | 2 Unlikely | 4 Major | 8 | 1 Rare | 4 Major | 4 | 2024-09-26
3793 | 2023-07-03 | Shared Services (Radiology and Pathology Services) | Patients | Vascular Radiology Reporting | 3 Possible | 4 Major | 12 | 2 Unlikely | 2 Minor | 4 | 2024-04-01
3828 | 2023-08-22 | Shared Services (Radiology and Pathology Services) | Patients | Wrightington Room 1 Radiography Equipment: Risk of Failure | 3 Possible | 3 Moderate | 9 | 1 Rare | 2 Minor | 2 | 2024-04-01